## Today_Bugs_Detailed
Bug ID | Title | Project Name | Module / Feature | Reported By | Assigned To | Severity | Priority | Environment |  | Status | Issue Type | Steps to Reproduce | Expected Result | Actual Result | Test Data | Attachments | Reported Date | Comments / Notes | Final Status
BUG_PROFILE_001 | Limited fields in Edit Profile | DAS Professional App | Profile → Update Personal Details | Shubham Yadav | Dev Team | Minor | Medium | Android | v1.0.0 | New | UI / Functional | 1. Launch the app | User should be able to edit name, phone number, email, and other personal details | Only Name and Language fields are available | Professional account | https://drive.google.com/file/d/11xb8jD2VsJLGRe3FwHaOkCogUYvnb5xi/view?usp=drive_link | 22-Dec-2025 | Add missing editable fields | Not Fixed
2. Login with valid professional account
3. Go to Profile tab
4. Open My Profile
5. Tap on Update Personal Details screen
BUG_PROFILE_002 | No remove option for profile image | DAS Professional App | Profile → Update Personal Details | Shubham Yadav | Dev Team | Minor | Medium | Android | v1.0.0 | New | UI / Functional | 1. Login to app | User should have an option to remove/delete profile image | Only replace option is available, no remove option | Profile image exists | N/A | 22-Dec-2025 | Add remove profile image option | Not Fixed
2. Navigate to Profile → My Profile
3. Open Update Personal Details
4. Tap profile image edit icon
Not Fixed
BUG_PROFILE_003 | Profile image auto-saved without confirmation | DAS Professional App | Profile → Update Personal Details | Shubham Yadav | Dev Team | Major | High | Android | v1.0.0 | New | Functional / UX | 1. Open Update Personal Details | Image should be saved only after user confirmation | Image gets saved automatically without Save option | Any image file | N/A | 22-Dec-2025 | Add Save/Confirm button
2. Tap profile image edit icon
3. Select image from gallery or camera
BUG_REG_004 | No validation message for Languages Known | DAS Professional App | Registration → Professional Details | Shubham Yadav | Dev Team | Minor | Medium | Android | v1.0.0 | New | Validation | 1. Open DAS Professional App | Validation message should be shown for Languages Known field | No error message is displayed | New registration | https://drive.google.com/file/d/1UE7p4qYajVCuJuR6XlY7afAkIoWZ7f4X/view?usp=drive_link | 22-Dec-2025 | Add mandatory field validation | Fixed
2. Go to Register Now screen
3. Fill all mandatory fields except Languages Known
4. Tap Continue
BUG_REG_005 | Gender field has limited options | DAS Professional App | Registration → Personal Details | Shubham Yadav | Dev Team | Minor | Medium | Android | v1.0.0 | New | UI / UX | 1. Navigate to Register Now screen | Gender dropdown should include inclusive options | Only Male and Female options are shown | New registration | https://drive.google.com/file/d/1roOpprjvK_YQQTdLp47bQu3XF_dR_s6O/view?usp=drive_link | 22-Dec-2025 | Add Other / Prefer not to say | Fixed
2. Tap on Gender dropdown
BUG_REG_006 | Email field accepts invalid special characters | DAS Professional App | Registration → Personal Details | Shubham Yadav | Dev Team | Major | High | Android | v1.0.0 | New | Validation | 1. Go to Register Now screen | Invalid email should be rejected with error message | Invalid email is accepted without validation | hhrjhfggda#*#///???%$!@gmail.comdfdfg | https://drive.google.com/file/d/1JYOwGSEtpBgkRGvINUwrjY0YPfD-T7K3/view?usp=drive_link | 22-Dec-2025 | Apply email regex validation | Fixed
2. Enter invalid email with special characters
3. Tap Continue
BUG_ORDER_007 | PIN not cleared after invalid entry | DAS Professional App | Orders → Start Service | Shubham Yadav | Dev Team | Minor | Medium | Android | v1.0.0 | New | Functional / UX | 1. Open an ongoing order | PIN fields should be cleared after invalid PIN message | Previously entered PIN remains in fields | Invalid PIN (e.g. 1234) | https://drive.google.com/file/d/1Qv6Sq9b2ZsbSC419jR3dZ3hbjXQhW4pb/view?usp=drive_link | 22-Dec-2025 | Clear PIN fields on error | Not Fixed
2. Tap Start Service
3. Enter incorrect 4-digit PIN
4. Observe input fields after error
BUG_REG_008 | Error message is displayed along with continuous loading indicator during registration | DAS Professional App | Registration | Shubham Yadav | Dev Team | Major | High | Android | v1.0.0 | New | Functional/UX | 1. Launch the DAS Professional App | If an error occurs during registration, the app should: | The app displays an error message while the loading symbol continues to spin, creating confusion and blocking further user action. | Valid registration details | https://drive.google.com/file/d/1hVKMnoi9uY15GFTDKKSiQSCmWtxOTKnr/view?usp=drive_link | 22-Dec-2025 | Loader is not dismissed when error response is received, leading to poor user experience and unclear system state | Fixed
[12 empty] | 2. Navigate to Register Now screen | • Stop the loading indicator
[12 empty] | 3. Fill all required details correctly | • Display a clear error message
[12 empty] | 4. Tap on Continue / Register button | • Allow user to retry the action
5. Observe the screen behavior
MOB-BUG-009 | Mark As Completed option not working on Create Quote screen | DAS Professional Application | Create Quote → Service Completion | Shubham Yadav | Mobile Development Team | Major | High | Android Mobile App ¦ LTE / 5G | v1.0.0 | New | Functional | 1. Open DAS Professional Application | Service should be marked completed and status updated. | No action occurs on tapping Mark As Completed. | Quote created with service details | https://drive.google.com/file/d/1-kNRfgvFBOM7A2sEjmVRMR59ESHyWgFR/view?usp=drive_link | 22-12-2025 | Blocks service completion flow | Fixed
2. Login as professional
3. Accept a service request
4. Navigate to Create Quote screen
5. Enter service details
6. Tap Mark As Completed option
MOB-BUG-010 | Validation error persists even after entering valid quote details | DAS Professional Application | Create Quote → Validation | Shubham Yadav | Mobile Development Team | Major | High | Android Mobile App ¦ LTE / 5G | v1.0.0 | New | Functional / UX | 1. Open DAS Professional Application | Validation error should clear and user should proceed. | Validation error message still appears. | Service: Cleaning ¦ Cost: 500 | https://drive.google.com/file/d/19rTJNK2n7TdCYWWjAWcNsKXDkebtBQXh/view?usp=drive_link | 22-12-2025 | Form validation state not reset | Not Fixed
2. Login as professional
3. Navigate to Create Quote
4. Submit quote without entering details
5. Enter valid service title and cost
6. Tap Review Quote again
MOB-BUG-011 | Loader remains visible in Completed Orders section after data load | DAS Professional Application | All Orders → Completed | Shubham Yadav | Mobile Development Team | Minor | Medium | Android Mobile App ¦ LTE / 5G | v1.0.0 | New | UI / UX | 1. Open DAS Professional Application | Loader should disappear once data is loaded. | Loader continues to display after data load. | Completed orders list | https://drive.google.com/file/d/15D-Ud-LSsVa0rSQHV962tQschQmTFBwY/view?usp=drive_link | 22-12-2025 | Improper loader state handling | Not Fixed
2. Login as professional
3. Navigate to All Orders
4. Select Completed status
5. Wait for orders to load
Not Fixed
MOB-BUG-012 | Loader remains visible in Reached Your Location orders | DAS Professional Application | All Orders → Reached Your Location | Shubham Yadav | Mobile Development Team | Minor | Medium | Android Mobile App ¦ LTE / 5G | v1.0.0 | New | UI / UX | 1. Open DAS Professional Application | Loader should stop after orders are loaded. | Loader remains visible at bottom. | Reached location orders | https://drive.google.com/file/d/1cnJH_iHUy_Wv0cEeKwuODl0Q4Qa6cegh/view?usp=drive_link | 22-12-2025 | Same issue seen in Completed orders
2. Login as professional
3. Navigate to All Orders
4. Select Reached Your Location status
5. Wait for orders to load
MOB-BUG-013 | Completed orders list view disappears when completed task count increases | DAS Professional Application | Completed Orders → Order List View | Shubham Yadav | Mobile Development Team | Major | Medium | Android Mobile App ¦ LTE / 5G | v1.0.0 | New | UI / UX | 1. Open DAS Professional Application | List view should remain stable regardless of number of completed tasks | The list view disappears partially or completely | Professional account with multiple completed services | https://drive.google.com/file/d/1PQjT_6Mlkd5L9hgBXrD_YoGbrC2H-Rsy/view?usp=drive_link | 22-12-2025 | Possible issue with list height calculation, pagination, or scroll container | Not Fixed
2. Login with a professional account
3. Navigate to Completed Orders section
4. Ensure there are multiple completed services (higher count)
5. Scroll through the completed orders list
6. Observe the list view behavior
MOB-BUG-014 | Ongoing orders list not refreshing after service completion | DAS Professional Application | Ongoing Orders | Shubham Yadav | Mobile Development Team | Major | High | Android Mobile App ¦ LTE / 5G | v1.0.0 | New | Functional / UX | 1. Open DAS Professional Application | Remaining ongoing services should still be visible automatically. | No Orders Yet message shown until manual refresh. | Multiple ongoing services | https://drive.google.com/file/d/1Wcy_OB2cwuAMjncWDWIwYA1IZ2bc3Hy5/view?usp=drive_link | 22-12-2025 | List state not refreshed automatically | Not Fixed
2. Login as professional
3. Ensure multiple ongoing services exist
4. Complete one service
5. Navigate back to Ongoing tab