## Master Bug Report
Bug ID | Title | Project Name | Module / Feature | Reported By | Assigned To | Severity | Priority | Environment | Build / Version | Status | Issue Type | Steps to Reproduce | Expected Result | Actual Result | Test Data | Attachments | Reported Date | Comments / Notes | Final Status
DAS-BUG-UI-001 | Welcome message is displayed every time user navigates back | Domala Aide Services | Global Notification / Navigation | Shubham Yadav | Development Team | Medium | Medium | Web Application | Latest Build | Open | UI / Functional | 1. Open the Domala Aide Services web application. | Welcome message should be shown only once after login or initial landing. | Welcome message is shown every time user navigates back. | Valid user credentials | https://drive.google.com/file/d/125_PR9LgcML4KUjPU06EduCae6PMiNpn/view?usp=drive_link | 2025-12-24 | Message is triggered on every page load. | Not Fixed
2. Log in using valid credentials.
3. Navigate to any internal page such as Services or Profile.
4. Click the browser back button or in-app back navigation.
5. Repeat navigation between pages.
6. Observe the welcome message popup.
DAS-BUG-FUNC-002 | Existing user service details are not loading properly | Domala Aide Services | Service Management / Vendor Services | Shubham Yadav | Development Team | High | High | Web Application | Latest Build | Open | Functional | 1. Log in to admin/vendor panel using an existing user account. | All previously saved services for existing users should load correctly. | Service data is missing or partially loaded for existing users while new users work fine. | Existing and new vendor accounts | https://drive.google.com/file/d/1xfjjOh2JpvKQFBi_c1NddBaZHYA07SCp/view?usp=drive_link | 2025-12-24 | Possible data mapping or API issue. | Not Fixed
2. Navigate to Services or Service Management section.
3. Observe the list of services added previously.
4. Log out and log in using a newly created user account.
5. Navigate to the same Services section.
DAS-BUG-SEC-003 | Deleted user account is still accessible | Domala Aide Services | User Account Management / Authentication | Shubham Yadav | Development Team | Critical | High | Web & Mobile Application | Latest Build | Open | Security / Functional | 1. Log in to DAS Professional mobile application. | Deleted account should be completely deactivated and login should be blocked. | Deleted account still exists in admin panel and user can log in again. | Deleted user credentials | https://drive.google.com/file/d/1-uNG8E4QDSBBKeAQBeIb3Gflu34bsk1V/view?usp=drive_link | 2025-12-24 | Critical security and data integrity issue. | Functionality
2. Navigate to account settings.
3. Delete the user account.
4. Log out of the application.
5. Attempt to log in again using the same credentials.
6. Check admin panel for deleted account presence.
DAS-BUG-FUNC-004 | Duplicate service slider created on multiple Save clicks | Domala Aide Services | Admin Panel → Service Sliders | Shubham Yadav | Development Team | Medium | Medium | Web Admin Panel | Latest Build | Open | Functional | 1. Log in to Admin Panel. | Only one service slider should be saved per submission. | Multiple duplicate slider entries are created. | Valid image file | https://drive.google.com/file/d/1YMKDOxwej2s0wjypl1nkqpy0_8Oi7yED/view?usp=drive_link | 2025-12-24 | Save button is not disabled after first click. | Not Fixed
2. Navigate to Home Services Module → Service Sliders.
3. Click Add Service Slider.
4. Upload image and fill required fields.
5. Click Save button multiple times quickly.
DAS-BUG-FUNC-005 | Newly added category not visible in user application | Domala Aide Services | Categories | Shubham Yadav | Development Team | High | High | Web Admin & User App | Latest Build | Open | Functional | 1. Log in to Web Admin Panel. | Newly added active category should be visible in user app. | New category is not displayed in user application. | Active category data | https://drive.google.com/file/d/1tlF2PSYp7G3ESfcJKJ6pQ3A62gNq5NiT/view?usp=drive_link | 2025-12-24 | Possible API sync or cache issue. | Not Fixed
2. Navigate to Home Services Module → Categories.
3. Add a new category and set status as Active.
4. Save the category successfully.
5. Open the User Application.
6. Navigate to Services section.
DAS-BUG-FUNC-006 | Sub-category for new category not visible in user app | Domala Aide Services | Sub Categories | Shubham Yadav | Development Team | High | High | Web Admin & User App | Latest Build | Open | Functional | 1. Log in to Web Admin Panel. | Sub-category should be visible under its respective category. | Sub-category is not displayed in user application. | Active sub-category data | https://drive.google.com/file/d/1KCZgCvCbw4Jz917poTiNR8NZM2ej2pgn/view?usp=drive_link | 2025-12-24 | Category ID mapping issue suspected. | Not Fixed
2. Create a new category with Active status.
3. Navigate to Sub Categories.
4. Create a sub-category under the new category.
5. Save the sub-category.
6. Open User Application and navigate to Services.
ADM-VC-STATUS-007 | Status in Version Control shown as 0/1 instead of Active/Inactive | Web Admin Panel | Version Control → Status Field | QA Team | Development Team | Minor | Medium | Web Admin (QA) | v1.x | New | UI Bug | 1. Login to Admin Panel | Status should display as Active or Inactive | Status is displayed as numeric values 0 or 1 | Any version record | N/A | 2025-12-26 | UI should map 1 → Active and 0 → Inactive | Fixed
2. Navigate to Version Control module
3. Observe Status column
ADM-VND-ASSIGN-008 | Unable to assign service to vendor created by user from Admin Panel | Admin Panel | Vendor Management → Service Assignment | QA Team | Development Team | Critical | High | QA | v1.x | New | Functional Bug | 1. Login to Admin Panel | Service should be assigned successfully | Service is not assigned to vendor | Vendor: User-created | https://drive.google.com/file/d/1v9u_KWLMi5Hb99q6XxUJEeu2g-0dOCcV/view?usp=drive_link | 2025-12-26 | Issue occurs only for user-created vendors | Fixed
2. Go to Vendor Management
3. Select user-created vendor
4. Try assigning service
5. Save
NOTIF-PUSH-009 | Push notifications not visible in Notification module | Customer Application | Notifications → Push Notifications | QA Team | Development Team | Major | High | QA | v1.x | New | Functional Bug | 1. Perform action triggering notification | Notification should appear in module | Notification not displayed in module | Test user account | https://drive.google.com/file/d/19SG0fXl-L8AM0UndEjUG3-NOu7uGUX8-/view?usp=drive_link | 2025-12-26 | Push received but not synced to module | To Be Tested
2. Receive push
3. Open Notification module
DAS-ADM-UI-010 | Admin create/update success without redirect | Domala Aide Services | Admin Management | Shubham Yadav | Dev Team | Medium | Medium | Web |  | New | Functional/UI | 1. Login as Super Admin | System should redirect to Admin listing page after successful save | Success message is shown but page does not redirect | Valid admin data | https://drive.google.com/file/d/1XHO39OsA34txGUpFTUp1NZhOzLB0k8Y3/view?usp=drive_link | 15-Dec-2025 | Navigation handling missing | Functionality
2. Navigate to Admin Control Panel → Users Management
3. Click Add New Admin or Edit existing Admin
4. Enter valid details
5. Click Save / Update
DAS-SV-VAL-011 | Mobile field accepts more than allowed digits | Domala Aide Services | Service Vendors | Shubham Yadav | Dev Team | Medium | High | Web |  | New | Validation | 1. Login as Admin | Mobile field should restrict input to valid 10-digit number | Field allows entering more than allowed digits | 345678987654334 | https://drive.google.com/file/d/1UELhVlcI7Mlk70pJ-v440NUbiEyHcBFe/view?usp=drive_link | 15-Dec-2025 | Input validation missing | Fixed
2. Navigate to Home Services Module → Service Vendors
3. Click Add Service Provider
4. Enter more than 10 digits in Mobile field
DAS-SV-FLT-012 | Status filter value not retained | Domala Aide Services | Service Vendors | Shubham Yadav | Dev Team | Medium | Medium | Web |  | New | UI/Functional | 1. Login as Admin | Selected status should remain visible in dropdown | Dropdown resets to Select Status | Status = Active | https://drive.google.com/file/d/1XnGIy5qPjN5kUh9JtdDPbytxtFHCA99R/view?usp=drive_link | 15-Dec-2025 | Filter state not preserved | Fixed
2. Navigate to Service Vendors list page
3. Select Status filter
4. Click Submit
DAS-ADM-UI-013 | Search bar disabled after using Print option | Domala Aide Services | Manage Admin Settings | Shubham Yadav | Dev Team | Medium | Medium | Web |  | New | UI | 1. Login as Admin | Search bar should remain enabled | Search bar becomes disabled | N/A | https://drive.google.com/file/d/1DGrpQb__dDgTDW7vNwzuXGYSBOIJSsZM/view?usp=drive_link | 15-Dec-2025 | UI state not restored | Fixed
2. Navigate to Admin Control Panel → Manage Admin Settings
3. Click Print
4. Return back
DAS-FAQ-DEF-014 | Display Order field pre-filled by default | Domala Aide Services | FAQ Management | Shubham Yadav | Dev Team | Low | Medium | Web |  | New | Functional | 1. Login as Admin | Display Order field should be empty | Field is pre-filled with value 10 | N/A | https://drive.google.com/file/d/1wd21UFuRoo_V2gm8gPYI7PJ0rhiwExPJ/view?usp=drive_link | 15-Dec-2025 | May cause duplicate ordering | Fixed
2. Navigate to Masters → FAQ Management
3. Click Add FAQ
DAS-MINI-FUN-015 | Active/Inactive status missing in Mini Category creation | Domala Aide Services | Mini Categories | Shubham Yadav | Dev Team | Medium | Medium | Web |  | New | Functional | 1. Login as Admin | System should provide Active/Inactive option | No status option available | N/A | https://drive.google.com/file/d/1sz34CIbqqg5vTz5XMRws2yptUmaIMzQF/view?usp=drive_link | 15-Dec-2025 | Default status unclear | Functionality
2. Navigate to Mini Categories
3. Click Add
DAS-UI-UX-016 | Unnecessary sort icon shown in Action column | Domala Aide Services | Listing Pages | Shubham Yadav | Dev Team | Low | Low | Web |  | New | UI/UX | 1. Login as Admin | Action column should not show sort icon | Sort icon displayed without functionality | N/A | https://drive.google.com/file/d/1qjM9u1a0vNXvfWlPclQiJzIBvb3WlapO/view?usp=drive_link | 15-Dec-2025 | Creates UI confusion | Fixed
2. Open any listing page
3. Observe Action column
DAS-UI-RESP-017 | Sidebar logo not visible in expanded state | Domala Aide Services | Sidebar Menu | Shubham Yadav | Dev Team | Low | Medium | Web |  | New | UI/Responsive | 1. Login as Admin | Logo should be visible | Logo disappears | N/A | https://drive.google.com/file/d/1iM8mZ_3hUgNh0Ybyy2MPIq4d2aCMUa3F/view?usp=drive_link | 15-Dec-2025 | CSS/layout issue | Fixed
2. Expand sidebar menu
DAS-SV-UI-018 | Update/Delete actions not displayed properly | Domala Aide Services | Service Vendors | Shubham Yadav | Dev Team | Medium | Medium | Web |  | New | UI | 1. Login as Admin | Edit/Delete actions should be visible | Actions misaligned | Existing vendors | https://drive.google.com/file/d/1XXevOS8Q3tajsucsSnosdsv4G7vngByI/view?usp=drive_link | 15-Dec-2025 | Usability issue | Fixed
2. Navigate to Service Vendors
3. Observe Action column
ADM-VC-STATUS-019 | Status in Version Control shown as 0/1 instead of Active/Inactive | Web Admin Panel | Version Control → Status Field | QA Team | Development Team | Minor | Medium | Web Admin (QA) | v1.x | New | UI Bug | 1. Login to Admin Panel | Status should display as Active or Inactive | Status is displayed as numeric values 0 or 1 | Any version record | N/A | 2025-12-26 | UI should map 1 → Active and 0 → Inactive | Fixed
2. Navigate to Version Control module
3. Observe Status column
ADM-VND-ASSIGN-020 | Unable to assign service to vendor created by user from Admin Panel | Admin Panel | Vendor Management → Service Assignment | QA Team | Development Team | Critical | High | QA | v1.x | New | Functional Bug | 1. Login to Admin Panel | Service should be assigned successfully | Service is not assigned to vendor | Vendor: User-created | https://drive.google.com/file/d/1v9u_KWLMi5Hb99q6XxUJEeu2g-0dOCcV/view?usp=drive_link | 2025-12-26 | Issue occurs only for user-created vendors | Fixed
2. Go to Vendor Management
3. Select user-created vendor
4. Try assigning service
5. Save